miniMUNC Template -- Based off of the miniMUNC 2022 Timeline

Date	Goal	Status
6/13	Send out miniMUNC committee suggestion form
7/09	Meeting with Lower Sec to decide committees and outline their roles / these will be less intense for miniMUNC compared to StuyMUNC / two of each type of committee / placards, name tags, overseeing committees (getting people to do what they’re supposed to and on time), maybe making the food guide for the area
7/15	Email Mr. Mykolyk about booking 1st (auditorium, lecture hall A and B) and 6th floor (including library) for October 22nd + schedule a meeting with Mykolyk
7/17	miniMUNC committee descriptions due and Dais application sent out
7/24	Dais applications due
7/25	Dais selected
7/26	Release Dais and have lower sec create group chats
7/31	Intro letters, committee information, committee descriptions due
8/10	Spots spreadsheet, committee positions due
8/12	Lower-sec check-in meeting, discuss logistics with lower-sec
8/24	Committee background due
8/27	Editing and finalizing due for dais, placards and name tags due for lower sec
8/28	A&E look over everything and put it onto website
8/29	Send email to schools about miniMUNC
8/29	Ask Upper-sec + two someclassmen to lead miniMUNC workshops
9/10	Send intro email
9/11	Order the supplies (pens, folders, name tags, placards from staples)
10/3, 10/6, 10/10, 10/13	DGs and Lower Sec StuyMUNC fold placards and assemble name tags during MUN meetings / (IMPORTANT) Ask teachers to come in into the building on the day of the conference
10/17	Check in with workshop presenters
10/20	Daises debrief during MUN meetings and loose ends are tied up
10/22	MINIMUNC 2022 LETS GO!